## Task List
	Project Name	Housing Fees
	Project Manager	Mohamed Abd elghafar
	Date	05/01/2022
	Version	1
- TASKS
Task No.	Task Description	Estimation/Hr	Dependency	Assign To	Task Status	Start Date	Finish Date	Actual Finsh	Notes
1	Use case 6
1.1	Rejection Reason – Drop down list	2.5		Praveen-Zeeshan	Assigned	01/06/2022	01/10/2022
1.1.1	Drop down list in Page (Remarks Field Intact)				Assigned
1.1.2	Rejection Reason UI Config Page				Assigned
2	Use case 7
2.1	Time span in working days for each request	4		Vijay-Zeeshan	Assigned	01/06/2022	01/11/2022
2.1.1	Column Time Span in Report				Assigned
2.1.2	Holiday UI Config Page				Assigned
3	Use case 8
3.1	Add time span as measure and filter in Report	1.5		Vijay-Zeeshan	Assigned	01/12/2022	01/13/2022
3.1.1	Report add Filter for Time Span				Assigned
4	Use case 9
4.1	Notification for Urgent Requests	6		Praveen-Zeeshan	Assigned	01/10/2022	01/18/2022
4.1.1	Notification 1 to mark red for Urgent Request				Assigned
4.1.2	Notification 2 to send email for Urgent Request-Scheduler with time configuration				Assigned
4.1.3	Log request for which email is sent.				Assigned
5	Use case 10
5.1	Hyperlink to access DEWA system from back end	2.5		Vijay-Zeeshan	Assigned	01/13/2022	01/17/2022
5.1.1	Parameter UI Config Page, Key Value				Assigned
6	Use case 11
6.1	Add user manual to main screen	0.5		Vijay-Zeeshan	Assigned	01/17/2022	01/18/2022
6.1.1	Add User manual download option				Assigned
6.1.2	The manual path should be added as Key in Parameter Page				Assigned
7	Security Issues – Medium
7.1	Cross-Site Request Forgery	3		Vijay-Zeeshan	In Progress	01/18/2022	01/21/2022
7.2	Missing Secure Attribute in Encrypted Session (SSL) Cookie				In Progress